## Slide 1: Ending Street Homelessness in Vanguard Cities Overarching Research and Evaluation Project funded by OAK Foundation
Background, Definitions, Research Questions, Methods, Tasks, Timing
Prof. Suzanne Fitzpatrick, I-SPHERE, Heriot-Watt University, Edinburgh, UK
Prof. Volker Busch-Geertsema, GISS, Association for Innovative Social Research and Social Planning, Bremen, Germany
IGH 2019 Vanguard City Summit 5-6 September, 2019

## Slide 2: Outline of Presentation
Background
Definitions
Measurement
Research questions
Methods
Tasks
Timing
Small grants programme
Notes: 2

## Slide 3: Background
Project will monitor progress towards the achievement of goals set by Vanguard Cities to end or reduce street homelessness by 31st December 2020, and evaluate how these goals are achieved.
Monitoring progress requires:
  a clear definition of what it means to “end homelessness”, and
  a reliable means of measuring trends in street homelessness and progress towards the specified goal
Evaluation requires:
  in-depth, qualitative case study work
  realistic evaluation: “What works, for whom, in what circumstances?”
Funding (by Oak foundation) was confirmed end of last week.

## Slide 4: Goals
All Vanguard Cities selected one of the following goals in IGH’s A Place to Call Home initiative
  To end street homelessness across the entire city.
  To end street homelessness in a particular neighbourhood or within a certain subpopulation of the city.
  To achieve a specified reduction in street homelessness in the city of 25%, 50% or 75%.
“Street homelessness” was defined as sleeping in the circumstances described in Categories 1a-d of the IGH ‘Global Homelessness Framework’ (see next slide), where relevant adding those living in tents/encampments.

## Slide 5: IGH Global Framework For Understanding Homelessness
 | Category |  | Subcategory
1 | People without accommodation | 1 (a) | People sleeping in the streets or in other open spaces (such as parks, railway embankments, under bridges, on river banks, in forests, etc).
 |  | 1 (b) | People sleeping in public roofed spaces or buildings not intended for human habitation (such as bus and railway stations, taxi ranks, derelict buildings, public buildings, etc.)
 |  | 1 (c) | People sleeping in their cars, rickshaws, open fishing boats and other forms of transport
 |  | 1 (d) | 'Pavement dwellers' - individuals or households who live on the street in a regular spot, usually with some form of makeshift cover.

## Slide 6: Definitions
Street homelessness has been successfully “ended” in a particular city – or in a specific neighbourhood or subgroup within that city - if there is nobody sleeping in the circumstances described above on an agreed date/during an agreed time window
Street homelessness has been successfully “reduced”, if the proportionate decrease in total numbers sleeping rough matches or exceeds the target set

## Slide 7: Minimum Measurement Requirements
Baseline, midpoint and final street counts (with complementary day time surveys), or alternatively use continuous data management systems which sufficiently cover the street population
Clearly document methodology used
Ensure coverage of street homelessness in the relevant city/neighbourhood/subgroup as completely as possible
Prevent double counting
Where possible, collect information about the total duration of street homelessness experienced by the individuals enumerated, and their basic characteristics

## Slide 8: Research questions I
To what extent are the Vanguard Cities adopting 'ending street homelessness' goals, and methodologies for monitoring progress towards these goals, which are consistent with the IGH programme requirements?
What (quantitative) evidence is there of progress toward the meeting of these goals, and how reliable is this evidence? What weaknesses or limitations are apparent in this evidence base?
What specific interventions are being used to reduce or eliminate street homelessness, and why were these chosen over alternative approaches?
Did the interventions deployed change after the launch of the IGH programme in the city? If so, why and what difference did that make?
What evidence is there (if any) to link specific interventions and any progress towards ending/reducing street homelessness in the city? What is it about these interventions that accounts for their success?

## Slide 9: Research questions II
Are there other (contextual) factors that have enabled or been barriers to the success of these specific interventions?
Are there differential rates of success for different street homeless groups, and what accounts for that?
Is there any evidence of repressive or otherwise inappropriate methods being used to pursue the 'ending street homelessness' goals, or of displacement effects?
Are there key components of success, and failure, that can be identified across the Vanguard Cities and provide lessons for future cohorts of cities?
What plans are there for sustaining any reductions identified? How realistic are these plans?
What difference (if any) did involvement in the IGH programme make in the city? What is the most useful role that IGH can play in supporting city's efforts to end street homelessness?

## Slide 10: Methods
  The overarching evaluation aims to integrate the lessons from across the 13 Vanguard Cities
  It is based on the assumption that local researchers will conduct the on-the-ground research in each city, and feed the required quantitative and qualitative data into the central research team for collation and analysis
  The success of the overarching evaluation therefore depends on good quality data from the local researchers.
  To help with this, the central research team will work with the Corra Foundation to disburse small grants to relevant local researchers (mainly in the Global South) to assist with their capacity to deliver the required data

## Slide 11: Tasks I
1. Agree/review with local researchers the qualitative + quantitative data they can supply. Bespoke for each city but envisage:
  Key policy documents
  Quantitative data on street homelessness trends + detailed account of definitions/methods
  Analysis of (repeated) key informant interviews
  Analysis of focus group discussions with frontline practitioners – use of vignettes (hypothetical but realistic examples)
  ‘User voice’ - ideally, qualitative data via interviews or discussion groups
  Ideally, we’d like to directly analyse some of the most important transcripts of interviews/discussions; have budgeted for translation

## Slide 12: Tasks II
2. Allocate small grants to support the research effort of local teams
3. Develop pro-forma for synthesizing each city’s evidence; and standardized research instruments to be used wherever possible (questionnaire, topic guide(s), vignettes)
4. Ongoing liaison with local researchers (we hope to make at least one visit to each city)
5. Collation and analysis of data from all 13 Cities
6. Interim and Final Reports:
the key components of success, and failure, across the cities - including those that are common across the cities and those which are distinctive to particular contexts
the added value of the IGH programme, and how this can be maximised
main lessons for future cohorts of cities

## Slide 13: Timetable
September-November 2019: Tasks 1-3
December- April 2020: Task 4-5
May 2020: Interim Report
June 2020- May 2021: Tasks 4-5
June 2021: Final Report

## Slide 14: Staff involved
Suzanne Fitzpatrick (HWU) – lead overall project + 2 cities
Volker Busch-Geertsema (GISS) – co-lead project + 4 cities
Beth Watts (HWU) – lead on 4 cities
Jenny Wood (HWU) – lead on 3 cities
Marie Reichenbach (GISS) – will support Volker‘s work
Jill McIntyre – project coordination, administration, liaison

## Slide 15: Corra Foundation Small Grants Programme
Corra Foundation is an charitable foundation with a 30 year history of grant-making and a relationship-based approach to supporting groups and organisations
Oak has made available £50,000 to be administered by Corra to support local research teams (mainly in Global South)
The central research team will work with local researchers, and liaise with Corra, in developing bespoke specifications of the data to be delivered using these funds
The central team will check that the data submitted by the local researchers meets the agreed specifications, and liaise with Corra about releasing the funds